## Revision Sheet
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Revision History
Version | Date | Updates/Changes | Confirmed by | Approved by
1 | 2014-07-18 | New Document | Confourmus | Jacob Borromeo
2 | 7/19/2014 | Editing Text | Confourmus | Jacob Borromeo
3 | 2014-08-15 | Resizing Project Scope | Confourmus | Jacob Borromeo

## Project Information
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Project Details
Project Name |  | U-EASY (USC-Everyday Assistant for Students and You)
Project Description |  | This is a software to be made as a partial requirement
for the [IT140] Software Engineering class. The software that the team
shall develop will apply the process of project management. This
Software will serve as a guide for users to properly locate buildings,
classrooms, and other school amenities. It will enable users to have access to
information regarding the buildings, rooms, departments, and facilities as
well as the availability of such. In addition, the software will also serve as a
personal tool for users as this will allow them to store notes, class schedules,
and important dates and reminders.
Project Team
| Project Leader | Jacob Borromeo (lupyduby@gmail.com)
| Project Members | Gio Niño Mendoza (Assistant Project Leader) (mendoza.gionino@gmail.com)
Julius Adrian Chin (Recorder) (jedaxxxx@gmail.com)
Mark Joseph Valenzona (Librarian and Configuration Manager)(valenzonama@gmail.com)
Software Process Model |  | Waterfall Model
Project Scope |  | Major Software Functionalities
*USC MAP
*ROOM INFORMATION(S)
*SEARCH
*SOFTWARE UPDATE (PENDING)
* BOOKMARKS
Deliverables
* Project Proposal
* Project Plan
* Meeting Minutes
* Weekly Progress Reports
* Review Record Cards
* Requirements Specification
* Design Documents
* Coding Guidelines
* Source Codes
* Unit Testing Specifications
* Unit Testing Results
* Integration Testing Specifications
* Integration Testing Results
* Working Software
* Project Completion Report
Note on D17: : Include email addresses

## Assumption_Constraints_Risks
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Assumptions
* | Number of members in the team are fixed all throughout the software engineering process.
* | Team members will abide by the guidelines identified within this plan.
* | Project team members will adhere to the Communications Plan.
* | Team members can render over time work if the need arises.
* | Payment of resources will be shared by all members of the team.
Constraints
* | Size of the team is fixed. Hence, no additional members may be recruited during the course of the software development.
Risks
Risk |  | Preventive Action/s | Countermeasure/s
* | Time of the students is consumed by their other subjects. | Members should follow the agreed number of | Overtime will be rendered if slippage to schedule
|  | hours to be allocated to the project. | occurs.
* | Funds diverted to other projects | Project leader will see to it that the team is still aligned with the budget schedule. | All team members will contribute for additional monetary resources.
* | The programmers aren't familiar with the programming language they will use. | Team Members will render time in studying the agreed programming language. | Time rendered in studying the programming language is monitored and is required.
* | Members aren't knowledgeable about the tools and other equipments needed. | Members will research and study for the tools needed in the project. | If needed, members will seek help from people with knowledge about the project.
Note on D16: : Abalquin: Actions to be done to prevent the risk from occurring.
Note on E16: : Abalquin: Action to do when a risk becomes an issue to lessen its impact to the project.

## Roles and Responsibilites
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Roles Assignment
* | Project Coordinator | Mr. Erwin Sarmiento
* | Project Leader | Jacob Borromeo
* | Assistant Project Leader | Gio Niño Mendoza
* | Minutes Recorder | Julius Adrian Chin
* | Configuration In-charge | Mark Joseph Valenzona
* | Developers | Jacob Borromeo
Gio Niño Mendoza
Julius Adrian Chin
Mark Joseph Valenzona
* | Tester/s | ALL TEAM MEMBERS
Responsibility Assignment Matrix (RAM)
Role/Responsibilities |  | Requirements Dev't | Project Planning | Design, Implementation, Testing | Project Monitoring and Control
* | Project Coordinator | Reviews and approves each version of the Requirements Specification. | Reviews and approves each version of the Project Plan and Schedule. | Checks the coding guidelines. Conducts design and code reviews | Checks Weekly Progress Report and Meeting Minutes. Checks for possible risks on a weekly basis.
Performs Process Audit
| Project Leader | Drives the creation, review and confirmation each version of the Requirements Specification. | Drives the creation, review and confirmation each version of the Project Plan and Schedule. | Spearheads creation of coding guidelines. Spearheads review of design documents and test cases for unit testing and internal testing/system testing. Spearheads initial code reviews. Approves the design document and codes. | Monitors and tracks status of tasks assigned. Conducts Weekly Progress Meeting. Prepares the Weekly Progress Report. Presents the Weekly Progress Report to class on a weekly basis. Monitors bug status until completion. Calls an emergency meeting when issues are encountered.
Collects, reviews and summarizes the process metrics.
* | Assistant Project Leader | Supports creation, review and confirmation of each version of the Requirements Specification. | Supports the creation, review and confirmation each version of the Project Plan and Schedule. | Assists creation of coding guidelines. Assists review of design documents and test cases for unit testing and internal testing/system testing. Assists/spearheads code reviews. | Assists and monitors developers on the technical issues of their respective modules.
Collects, reviews and summarizes the process metrics.
* | Minutes Recorder | Creates Meeting Minutes during the Requirements Development meetings and reviews. | Creates Meeting Minutes during the Project Planning meetings and reviews. | Creates Meeting Minutes for implementation activities meetings and reviews. | Creates Meeting Minutes during Weekly Progress Meeting and emergency meetings.
Submits time spent in Meeting Minutes Recording to the Project Leader.
* | Librarian | Checks if the versioning and the updates of the Requirements Specification are stored and kept tracked. Registers documents related to this phase. | Checks if the versioning and the updates of the Project Plan are stored and kept tracked. Drives the creation of folder structure of the project. Registers documents related to this phase. Formulates the DM Plan. | Checks if the versioning and the updates of the test specification and results are stored and kept tracked. Stores Release Notes for Alpha and Final Release. Registers documents related to this phase. | Reminds the team on document-related processes, if necessary. Checks if all document versioning and template items are filled-up. Registers documents related to this phase.
Submits time spent in Data Management to the Project Leader.
* | Configuration In-charge | Supports creation, review and confirmation of each version of the Requirements Specification. | Discuss with the team process of coding guidelines, structure, and integration. Discuss with the team process of database guidelines. Formulates the CM Plan. | Makes sure that the code integration process is followed. Manages the database. Prepares the build for unit and integration testing activities. Prepares Release Notes for Alpha and Final Release. Release the software. | Reminds the team on configuration processes, if necessary. Checks if all document versioning and template items are filled-up.
Submits time spent in Configuration Management to the Project Leader.
* | Developer | Supports creation, review and confirmation of each version of the Requirements Specification. | Supports creation, review and confirmation of each version of the Project Plan and Schedule. | Does design, coding, unit testing. Supports design, code and test cases review. Prepares unit testing test cases and performs unit testing. Fixes bugs. | Attends Weekly Progress Meetings and emergency meetings. Reports issues to the Project Leader (e.g. Task delayed, technical issues, etc.) Reports possible risk/s. Reports status of the assigned task to the Project Leader.
Submits the time spent in doing implementation-related activities to the Project Leader.
* | Tester/s | Reviews and confirms the Requirements Specification. | Reviews and confirms each version of Project Plan and Schedule. | Prepares the test cases, performs internal testing and do checking of the bug fixed. Note: Internal testing can be done in one OS or platform only. Reviews and confirms the design document and codes. Reports bugs. Checks fixed bugs. | Attends Weekly Progress Meetings and emergency meetings. Reports internal testing issues to the Project Leader (e.g. Task delayed, issues, etc.) Reports possible risk/s. Reports status of testing.
Submits the time spent in doing testing-related activities to the Project Leader.
Note on C18: : Abalquin: You may revise the responsibilities for each role as it applies to your team.
Note on F19: : Abalquin: Includes design, coding, unit testing, internal testing and system testing.

## Resources
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Resources Needed
Item | Cost
2 Desktop Computers | 0
4 Laptops | 0
MS Office (Excel, Word) | 0
Notepad | 0
Notepad++ | 0
Mozilla | 0
Eclipse | 0
Printing | 100
Yellow/white paper | 20
Bondpaper | 100
Pencil/ballpen | 20
Total Cost | 240

## Document Management
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Data Management
Main Location of the Documents | Mark Valenzona's Laptop, stored in Drive D:\Soft_Eng with the folder name "Confourmus"
Backup Location | Team email's dropbox account, Team email's google drive (accessible via mobile), and team's facebook group
Document Registration Procedure | 1. Request for template of the document should be sent to the Librarian via email to the Project Coordinator.
2. After creation of the document and before it is scheduled for review, Librarian stores official version to the library.
3. Librarian emails to Project Leader CC the team and Project Coordinator that he/she has stored the document to the library with official filename
4. After document is modified based on review, Librarian stores modified version to the library.
4. Librarian should notify Project Coordinator for succeeding versions of the document after it is already confirmed before storing to the library.
Filename Naming Convention | Format: | ProjectName_DocumentName_VersionNumber
If more than one word, capitalize the first letter of the word. If more than one word, don't separate the ProjectName with underscore. If more than one word, separate DocumentName with underscore.
| Examples: | DigitalOrganizer_Requirements_Specification_v1.00
Folder Structure | 00_Pre-development
Project Proposal
01_Project Planning
Project_Plan
Review Record Card
02_Requirements Specification
Requirements_Specification
Review Record Card
03_Design
General Design (Activity, Class, Sequence, Software Archi)
DB Design
ScreenDef
Review Record Card
04_Coding
Coding Guidelines
Review Record Card (from APL)
Unit Testing Specifications (blank, not yet filled up)
Integration Testing Specifications (blank, not yet filled up)
05_Testing
Unit Testing Results (filled up UTS)
UT Bug Report
Integration Testing Results (filled up ITS of own software)
IT Bug Report (own software)
06_Release
Internal Release Notes (3)
Alpha Release Notes
Beta Release Notes
07_Project Monitoring
Meeting Minutes
Weekly Progress Report
UT Status Monitoring
IT Status Monitoring (own software)
08_Project Closure
Project Completion Report
01_Meeting Minutes
02_Weekly Progress Report
02_Project Planning
Email Structure Template | Subject: | Precede the subject [IT140] with the process where it belongs:
[PLANNING] <Subject> Document Request/Document Registration
[REQ] <Subject> Document Request/Document Registration
[DESIGN] <Subject> Document Request/Document Registration
[CODING] <Subject> Document Request/Document Registration
[UNIT_TESTING] <Subject> Document Request/Document Registration
[INTEGRATION_TESTING] <Subject> Document Request/Document Registration
[REVIEW] <Subject> Document Request/Document Registration
[PMC] <Subject> Document Request/Document Registration
[OTHERS] <Subject> Document Request/Document Registration
| Deadline: | Date of submission of the action items.

## Configuration Management
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Data Management
Main Location of the Source Codes and Database | Gio Mendoza's Desktop, stored in Drive D:\Gio\IT140-Software_Engineering with the folder name "Confourmus"
Backup Location | Team email's dropbox account, Team email's google drive (accessible via mobile), and team's facebook group
Code Integration Procedure | 1. Code integration is made every Friday.
2. Before test cases are applied, testing is done only by error troubleshooting and assuring that the functionality works as expected.
3. The code for every release is stored separately from its older version. Folder naming is followed properly.
4. A team meeting will be conducted after every release for discussions and clarifications.
Filename Naming Convention | Format: | ProjectName_DocumentName
If more than one word, capitalize the first letter of the word. If more than one word, don't separate the ProjectName with underscore. If more than one word, separate DocumentName with underscore.
| Examples: | DigitalOrganizer_alarm_setting.java
Database Management Guidelines | 1. CM should be aware of all changes made to the database.
2. DB backup is performed every Friday
Email Structure Template | Subject: | Precede the subject with the process where it belongs:
[PLANNING] <Subject>
[REQ] <Subject>
[DESIGN] <Subject>
[CODING] <Subject>
[INT_TESTING] <Subject>
[SYS_TESTING] <Subject>
[DATA_CM] <Subject
[PMC] <Subject>
[OTHERS] <Subject>
| Deadline: | Date of submission of the action items.

## PMC
U-EASY (USC-Everyday Assistant for Students and You)
Project Plan
Project Monitoring and Control
Weekly Progress Meeting Schedule | Every Friday at 9:00 - 10:00am
Weekly Progress Submission | Every Monday night before 12MN.
Weekly Progress Submission In-charge | Jacob Borromeo or in his unavailability, Gio Niño Mendoza
Monthly Meeting Minutes Submission | Every 1st of the month before 12MN.
Monthly Meeting Minutes Submission In-charge | Julius Adrian Chin or in his unavailability, Jacob Borromeo