## Revision History
U-EASY |  | Review Record Card |  | Registration No.
|  |  |  | Version No. | 1
|  |  |  | Date | 2015-01-10
|  |  |  | No. of Sheets | 11
Revision History
Version | Author | Date | Remarks
1 | Julius Adrian Chin | 2014-12-20 | Initial RRC for Code Demo 2
2 | Julius Adrian Chin | 2015-01-10 | Added names on Implemented by columns and confirmation dates
**Please hide this sheet when this template is used.

## General Defect List
U-EASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-30
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## Search Module
U EASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-20 | 2014-12-20 | 2015-01-30
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1 | Search/Search Results | Search substring. Can search like words that are on the start, the middle and the end of the word |  |  | Search subtring implemented |  | Gio Niño Mendoza | 22：Coding mistake: Lack of implementation | 1：Lack of Investigation | 3：Coding | 3：Review Check Point of View Miss | 2015-01-05 | Jacob Borromeo
2 | Search/Search Results | When there are no results found, add a notification saying "No results found" |  |  | Shows notification "No Results Found" when no results are found |  | Gio Niño Mendoza | 22：Coding mistake: Lack of implementation | 1：Lack of Investigation | 3：Coding | 3：Review Check Point of View Miss | 2015-01-05 | Jacob Borromeo
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## USC Map Module
U EASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-30
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1 | Map | To close the popup when a marker is clicked, you have to click another marker to close the other one. Make it so that the user doesn't have to click another marker. |  |  | Click anywhere will close the open popup |  | Gio Niño Mendoza | 22：Coding mistake: Lack of implementation | 3：Lack of Consideration | 3：Coding | Reviewee disclosure miss | 2015-01-05 | Jacob Borromeo
2 | Map | Add label to the gates |  |  | added label |  | Gio Niño Mendoza | 22：Coding mistake: Lack of implementation | 3：Lack of Consideration | 3：Coding | Reviewee disclosure miss | 2015-01-06 | Jacob Borromeo
3 | Map | More zoom |  |  | Zoom implemented to level 18 |  | Gio Niño Mendoza | 22：Coding mistake: Lack of implementation | 3：Lack of Consideration | 3：Coding | Reviewee disclosure miss | 2015-01-07 | Jacob Borromeo
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## About Module
U EASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-28
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## Category Module
U EASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-30
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## Content Update Module
UEASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-30
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## View Amenities Information
UEASY |  | Date & Time | 2014-12-20 | 0.5 | Reviewee | Confourmus | Review Object(s) | UEASY v0.0.01 |  |  | Pre-reviewed by | Reviewed by | Confirmed by
[5 empty] | Reviewer(s) | Erwin Sarmiento |  |  |  |  | Jacob Borromeo | Erwin Sarmiento | Jacob Borromeo
[5 empty] | Confirmation Hours | 1
|  | Total Review Hours |  | 0.5 | Total Work Hours | 1.5 |  |  |  |  | 2014-12-19 | 2014-12-20 | 2015-01-28
No. | Defect Location | Comments |  |  | Countermeasure |  | Implemented by | Bug classification | Bug Cause | Cause Phase | Escape Cause | Date Confirmed | Confirmed By | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
Note on H4: Admin: After making modifications based on Project Coordinator`s Review, how many hours did it take for PL to confirm if all comments were implemented?

## Index
Bug classification
| Confirmation item | To be resolved or investigated after the review; MIC does not have enough information to decide whether a defect or not during the review meeting.
| Comment | Not a bug, defect or question. Possibly an item worth noting during the review. Formatting related points may be classified here.
1：Planning Mistake: Incomplete/insufficient estimation
2： Planning Mistake: Wrong input data
1：Requirements Mistake: Incomplete/insufficient requirement specification
2： Requirements Mistake: Wrong requirement specification
3：Design mistake: Lacking functionality
4：Design mistake: Unnecessary functionality
5：Design mistake: Wrong functionality
6：Design mistake: Unclear definition/description
7：Design mistake: Logic mistake
8：Design mistake: Structuralization mistake
9：Design mistake: Interface mistake
10：Design mistake: Standardization mistake
11：Design mistake: Lack of maintainability
12：Design mistake: Others
13：Test items/Test Specs mistake: Lacking item
14：Test items/Test Specs mistake: Unnecessary Item
15：Test items/Test Specs mistake: Wrong Item
20：Test items/Test Specs mistake: Others
22：Coding mistake: Lack of implementation
22：Coding mistake: Unnecessary implementation
23：Coding mistake: Conflicting/redundancy/race condition processing
24：Coding mistake: Memory management
25：Coding mistake: Infinite loop processing
29：Coding mistake: Initialization
30：Coding mistake: Interface
31 : Coding mistake: Data declaration
32 : Coding mistake: Data reference
33 : Coding mistake: Data setting
34 : Coding mistake: Data checking
35 : Coding mistake: Decision processing
36 : Coding mistake: Computation
37 : Coding mistake: Use of language
38 : Coding mistake: Performance
39 : Coding mistake: Standardization
40 : Coding mistake: Lack of Maintainability
41 : Coding mistake: Others
Bug Cause
-
1：Lack of Investigation
2：Mistake in Input Information (Lacking, Error, etc)
3：Lack of Consideration
4：Mistake in Judgement
5：Lack of Understanding (Standards, Technology)
6：Lack of Understanding (Programming Technology)
7：Communication Miss (Internal)
8：Communication Miss (External)
9：Careless Miss
10：Others
Cause Phase
-
0： Planning
1：Requirements
2：Design
3：Coding
4：Test Specs Creation
5：Existing (From reuse)
Escape Cause
-
1：No review
2：Not Enough Review Time
3：Review Check Point of View Miss
4：Reviewee Disclosure Miss
5：Problem in Review Method
6：Others