## Sheet1
U-EASY (USC-Everyday Assistant for Students and You)
Weekly Progress Report
December 23 - 29, 2014
Project Details
Project Name | U-EASY (USC-Everyday Assistant for Students and You) | Project Coordinator | Mr. Erwin Sarmiento
Start Date | 2014-12-23 | Project Leader | Jacob Borromeo
End Date | 2014-12-29 | Project Members | Gio Niño Mendoza (APL)
Julius Adrian Chin (Recorder)
Mark Valenzona (Configuration Manager and Librarian)
Project Status
Recent Milestone | DB Design, General Design
On-going Tasks | Modules to implement, UTS
Schedule | OK
Cost | OK
Process | OK
Accomplishments for the Week
Task | Target % | Actual Completion % | Comments
UTS
About | 100% | 100%
Category | 100% | 100%
USC Map | 100% | 100%
Content Update | 100% | 100%
Search | 100% | 100%
View Amenities Information | 100% | 100%
Modules to implement
Search | 100% | 96%
About | 100% | 98%
Category | 100% | 98%
Content Update | 100% | 0%
USC MAp | 100% | 55%
View Amenities Information | 100% | 15%
Percentage Status Reporting
Documentation Tasks/Coding/Testing |  | Study/Training/Research/Investigation/Installation/Setup
*Started | 10%
*Completed | 30% | Progress Percentage = (Used up Number of hours / Allocated Number of hours) x 100%
*Reviewed | 50%
*Updated | 80%
*Confirmed/Approved | 100%
Tasks for Next Week
Task | Target % | Actual Completion % | Comments
UTS
About | 100% | 100%
Category | 100% | 100%
USC Map | 100% | 100%
Content Update | 100% | 100%
Search | 100% | 100%
View Amenities Information | 100% | 100%
Modules to implement
Search | 100% | 96%
About | 100% | 98%
Category | 100% | 98%
Content Update | 100% | 0%
USC MAp | 100% | 55%
View Amenities Information | 100% | 15%
Project Data
SDLC Stage | Estimated Value | Actual Value | Comments
Project Cost | P0000.00
Project Planning Effort | 1 mm/pax | 4 mm
Requirements Dev't Effort | 1 mm/pax | 4 mm
Design Effort | 1 mm/pax | 4 mm
Coding Effort | 1.4 mm/pax | 5.6 mm
Unit Testing Effort | N/A | N/A
Integration Testing Effort | N/A | N/A
System Testing Effort | N/A | N/A