## Sheet1
U-EASY (USC-Everyday Assistant for Students and You)
Weekly Progress Report
July 15-21, 2014
Project Details
Project Name | U-EASY (USC-Everyday Assistant for Students and You) | Project Coordinator | Mr. Erwin Sarmiento
Start Date | 2014-07-15 | Project Leader | Jacob Borromeo
End Date | 2014-07-21 | Project Members | Gio Niño Mendoza (APL)
Julius Adrian Chin (Recorder)
Mark Valenzona (Configuration Manager and Librarian)
Project Status
Recent Milestone | Project Proposal
On-going Tasks | Project Planning
Schedule | OK
Cost | NA
Process | NA
Accomplishments for the Week
Task | Target % | Actual Completion % | Comments
Project Planning
Making New Document | 50% | 50%
Research & Study
Android | 100% | 60.71%
Setup
Eclipse | 100% | 50%
Percentage Status Reporting
Documentation Tasks/Coding/Testing |  | Study/Training/Research/Investigation/Installation/Setup
*Started | 10%
*Completed | 30% | Progress Percentage = (Used up Number of hours / Allocated Number of hours) x 100%
*Reviewed | 50%
*Updated | 80%
*Confirmed/Approved | 100%
Tasks for Next Week
Task | Target % | Actual Completion % | Comments
Editing Text for Project Planning | 80% | 50%
Practice Coding | 100% | 0%
Project Data
SDLC Stage | Estimated Value | Actual Value | Comments
Project Cost | P0000.00
Project Planning Effort | 1 mm/pax | 2 mm
Requirements Dev't Effort | 0.3 mm/pax | 1.2 mm | Acquiring the requirement slowly by slowly to save time in the future.
Design Effort | N/A | N/A
Coding Effort | N/A | N/A
Unit Testing Effort | N/A | N/A
Integration Testing Effort | N/A | N/A
System Testing Effort | N/A | N/A