## Sheet1
U-EASY (USC-Everyday Assistant for Students and You)
Weekly Progress Report
September 2 - 8, 2014
Project Details
Project Name | U-EASY (USC-Everyday Assistant for Students and You) | Project Coordinator | Mr. Erwin Sarmiento
Start Date | 2014-09-02 | Project Leader | Jacob Borromeo
End Date | 2014-09-08 | Project Members | Gio Niño Mendoza (APL)
Julius Adrian Chin (Recorder)
Mark Valenzona (Configuration Manager and Librarian)
Project Status
Recent Milestone | Requirements Dev't Effort
On-going Tasks | Screen Defenition
Schedule | OK
Cost | NA
Process | NA
Accomplishments for the Week
Task | Target % | Actual Completion % | Comments
Requirements Dev't Effort
USC MAP screens | 100% | 10%
Search screens | 100% | 10%
View Amenities Information screens | 100% | 10%
Category screens | 100% | 10%
Content Update screens | 100% | 10%
About screens | 100% | 10%
Screen Flow | 100% | 15%
Screen List | 100% | 15%
General Logic | 100% | 10%
Research & Study
Practice Coding | 100% | 100%
Percentage Status Reporting
Documentation Tasks/Coding/Testing |  | Study/Training/Research/Investigation/Installation/Setup
*Started | 10%
*Completed | 30% | Progress Percentage = (Used up Number of hours / Allocated Number of hours) x 100%
*Reviewed | 50%
*Updated | 80%
*Confirmed/Approved | 100%
Task | Target % | Actual Completion % | Comments
USC MAP screens | 100% | 10%
Search screens | 100% | 10%
View Amenities Information screens | 100% | 10%
Category screens | 100% | 10%
Content Update screens | 100% | 10%
About screens | 100% | 10%
Screen Flow | 100% | 15%
Screen List | 100% | 15%
General Logic | 100% | 10%
Practice Coding | 100% | 10%
Project Data
SDLC Stage | Estimated Value | Actual Value | Comments
Project Cost | P0000.00
Project Planning Effort | 1 mm/pax | 2 mm
Requirements Dev't Effort | 1 mm/pax | 4 mm
Design Effort | .5 mm/pax | 2 mm
Coding Effort | N/A | N/A
Unit Testing Effort | N/A | N/A
Integration Testing Effort | N/A | N/A
System Testing Effort | N/A | N/A